## GanttChart
[PPM Group Project] Project Schedule | [8 empty] | Gantt Chart Template © 2006-2018 by Vertex42.com.
[PPM Group]
| Project Start Date | 2019-01-01 |  |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19
| Project Lead | [7 empty] | 2018-12-31 | [6 empty] | 2019-01-07 | [6 empty] | 2019-01-14 | [6 empty] | 2019-01-21 | [6 empty] | 2019-01-28 | [6 empty] | 2019-02-04 | [6 empty] | 2019-02-11 | [6 empty] | 2019-02-18 | [6 empty] | 2019-02-25 | [6 empty] | 2019-03-04 | [6 empty] | 2019-03-11 | [6 empty] | 2019-03-18 | [6 empty] | 2019-03-25 | [6 empty] | 2019-04-01 | [6 empty] | 2019-04-08 | [6 empty] | 2019-04-15 | [6 empty] | 2019-04-22 | [6 empty] | 2019-04-29 | [6 empty] | 2019-05-06
 | time axis 2018-12-31 to 2019-05-12
WBS | TASK |  | PREDECESSOR | START | END | DAYS |  | WORK DAYS | time axis 2018-12-31 to 2019-05-12
1 | Backend Components |  |  |  | - |  |  | -
1.1 | Token based authentication for API routes |  |  | 2019-01-14 | 2019-01-25 | 12 |  | 10
1.2 | Database Migrations for Storing Users |  |  | 2019-01-14 | 2019-01-25 | 12 |  | 10
1.3 | Services for Generating Relevant Statistics |  |  | 2019-01-14 | 2019-01-31 | 18 |  | 14
2 | API |  |  |  | - |  |  | -
2.1 | Endpoint for Creating Users for the Monitoring Application |  |  | 2019-01-25 | 2019-02-03 | 10 |  | 6
2.1.1 | Endpoint for Listing Users |  |  | 2019-02-03 | 2019-04-15 | 72 |  | 51
2.1.2 | Endpoint for Adding Users |  |  | 2019-02-03 | 2019-04-15 | 72 |  | 51
2.1.3 | Endpoint for Removing Users |  |  | 2019-02-03 | 2019-04-15 | 72 |  | 51
2.1.4 | Endpoint for Updating Users |  |  | 2019-02-03 | 2019-04-15 | 72 |  | 51
2.2 | Endpoint for Adding Campuses |  |  | 2019-04-10 | 2019-04-17 | 8 |  | 6 | bar: 2019-04-10 to 2019-04-17
2.2.1 | Endpoint for Updating Campuses |  |  | 2019-04-10 | 2019-04-17 | 8 |  | 6 | bar: 2019-04-10 to 2019-04-17
2.2.2 | Endpoint for Listing Campuses |  |  | 2019-04-10 | 2019-04-17 | 8 |  | 6 | bar: 2019-04-10 to 2019-04-17
2.2.3 | Endpoint for Removing Campuses |  |  | 2019-04-10 | 2019-04-17 | 8 |  | 6 | bar: 2019-04-10 to 2019-04-17
2.3 | Endpoint for Adding Buildings |  |  | 2019-04-12 | 2019-04-22 | 11 |  | 7 | bar: 2019-04-12 to 2019-04-22
2.3.1 | Endpoint for Listing Buildings |  |  | 2019-04-12 | 2019-04-22 | 11 |  | 7 | bar: 2019-04-12 to 2019-04-22
2.3.2 | Endpoint for Updating Buildings |  |  | 2019-04-12 | 2019-04-22 | 11 |  | 7 | bar: 2019-04-12 to 2019-04-22
2.3.3 | Endpoint for Removing Buildings |  |  | 2019-04-12 | 2019-04-22 | 11 |  | 7 | bar: 2019-04-12 to 2019-04-22
2.4 | Endpoint for Listing Statistics |  |  | 2019-04-22 | 2019-04-24 | 3 |  | 3 | bar: 2019-04-22 to 2019-04-24
2.5 | Endpoint for Listing Alerts |  |  | 2019-04-20 | 2019-04-25 | 6 |  | 4 | bar: 2019-04-20 to 2019-04-25
2.5.1 | Endpoint for Updating Alerts |  |  | 2019-04-20 | 2019-04-25 | 6 |  | 4 | bar: 2019-04-20 to 2019-04-25
2.6 | Endpoint for Enrolling Cameras |  |  | 2019-04-20 | 2019-04-25 | 6 |  | 4 | bar: 2019-04-20 to 2019-04-25
2.6.1 | Endpoint for Removing Cameras |  |  | 2019-04-20 | 2019-04-25 | 6 |  | 4 | bar: 2019-04-20 to 2019-04-25
2.6.2 | Endpoint for Listing Cameras |  |  | 2019-04-20 | 2019-04-25 | 6 |  | 4 | bar: 2019-04-20 to 2019-04-25
2.7 | Endpoint for Viewing Users |  |  | 2019-04-10 | 2019-04-25 | 16 |  | 12 | bar: 2019-04-10 to 2019-04-25
3 | Front End |  |  |  | - |  |  | -
3.1 | Screen Designs (Stats, Administration and Dashboard) |  |  | 2019-01-15 | 2019-01-28 | 14 |  | 10
3.2 | Login Page for Web Application |  |  | 2019-01-14 | 2019-02-04 | 22 |  | 16
3.3 | Forgot Password Page For Web Application |  |  | 2019-01-14 | 2019-02-04 | 22 |  | 16
3.4 | Basic Dashboard for Web Application |  |  | 2019-01-14 | 2019-02-22 | 40 |  | 30
3.5 | Basic Statistics Page for Web Application |  |  | 2019-01-14 | 2019-02-22 | 40 |  | 30
3.6 | Basic Administration Interface for Web Application |  |  | 2019-01-14 | 2019-02-22 | 40 |  | 30
3.6.1 | Basic User Profile Page |  |  | 2019-01-14 | 2019-02-22 | 40 |  | 30
3.7 | First Draft of Web Application |  |  | 2019-01-17 | 2019-02-25 | 40 |  | 28
3.7.1 | Validation Errors for Web Application |  |  | 2019-02-25 | 2019-03-25 | 29 |  | 21 | bar: 2019-02-25 to 2019-03-25
3.8 | Second Draft of Web Application |  |  | 2019-02-25 | 2019-03-25 | 29 |  | 21 | bar: 2019-02-25 to 2019-03-25
3.9 | Completed Web Application |  |  | 2019-03-25 | 2019-04-22 | 29 |  | 21 | bar: 2019-03-26 to 2019-04-21
4 | Facial Recognition |  |  |  | - |  |  | -
4.1 | Camera application |  |  | 2019-01-14 | 2019-01-27 | 14 |  | 10 | bar: 2019-01-14 to 2019-01-27
4.2 | Facial detection |  |  | 2019-01-27 | 2019-03-10 | 43 |  | 30 | bar: 2019-01-27 to 2019-03-10
4.3 | Model training |  |  | 2019-01-27 | 2019-03-10 | 43 |  | 30 | bar: 2019-01-27 to 2019-03-10
4.4 | Facial recognition application |  |  | 2019-03-05 | 2019-04-13 | 40 |  | 29 | bar: 2019-03-03 to 2019-04-13
-
-
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.